## Sheet1
Potential Haddock Research Components (2021-2022)
May 17th 2021
T. Carruthers
# | Item | Description | Approx. days
1 | Conversion of assessments to operating models
a | WG Meetings | Additional WG Meetings associated with Haddock RT Delay | 7
b | WHAM2OM | A function in openMSE that takes a fitted WHAM model and converts this automatically to a functioning MSEtool operating model for closed-loop simulation testing of stock assessments, harvest control rules and management procedures | 15
c | HCR evaluation | Current harvest control rules for fisheries in the region are added to openMSE (including raw code for DFO users to modify) and tested against Haddock operating models | 15
d | Demonstration MP | A demonstration MP using survey indices is designed and tuned to haddock operating models and used to demonstrate the potential benefits of a simpler MP approach | 10 | spatial issues
e | CSAS Review | 5 days is enough time to develop the domestic reference points and present them at a CSAS process | 5 | 52000
2 | 4X Haddock assessment / operating model and MP testing
a | Preliminary Stock Assessment / Ref. Case OM | Currently available data (from previous assessment) are used to condition an reference case operating model (base case assessment) for 4X haddock (including a small selection of the key alternative reference grid OMs). This framework is either using RCM (SAMtool) which automatically creates an operating model object or, if using WHAM this would require 1a above. Regardless of the modelling approach, the code is provided open source and designed in a way that allows for easy update following newly processed fishery data. | 35
b | Index based MPs | Design and tune a set of survey index based MPs in addition to a status-quo representation of the current MP used in setting management advice | 15
c | Exceptional circumstances protocols | Identify problematic OMs (simulations) from #2a and establish exceptional circumstances protocols with sufficient statistical power to detect those | 10
60000
3 | The OM approach to EBFM (EBFM that can pass peer-review)
a | Specify OMs | Using WHAM or RCM, develop a set of OMs that span plausible scenarios for key ecosystem considerations such as recruitment regime shifts, somatic growth changes and changes in survival (e.g. density dependent survival or linked to abundance of other populations). | 35
b | Test status quo | EcoTest Step 1: Test whether there is a problem with the status quo system of providing management advice. Does the existing management system performance adequately given the scenarios in 3a? | 15
c | Develop and test ecosystem-ready HCRs | EcoTest Step 2: if status quo management does not perform adequately, develop harvest control rules that account for environmental covariates an test their performance under the scenarios of 1a. | 20
d | Develop and test exceptional circumstances protocols | EcoTest Step 3: In situations where status quo management does not perform adequately and the developed HCRs are ineffective in some scenarios, exceptional circumstances prototcols are identified that provide an early warning system that the data observed are consistent with situations that are problematic. | 20 | 90000
Note on C9: Wang, Yanjun: the DFO reference point will be produced from the WHAM2OM
Note on E12: Wang, Yanjun: $50k is doable
Note on B19: Wang, Yanjun: apply competitive funding